## Slide 1: Convention on the Conservation of European Wildlife and Natural Habitats Standing Committee ELEMENTS OF A POST-2020 EMERALD WORKPLAN Otars Opermanis & Marc Roekaerts

## Slide 2
Structure of the post 2020 workplan
Learning from evaluation of 2011-2020 workplan
Four elements (inter-linked tables) proposed
1. Targets
2. Strategic issues
3. Activities to reach targets
Appendix. Detailed planning framework
Workplan should not be a static document but can be updated as appropriate

## Slide 3
Table 1. Targets
Milestones | Phase I |  | Phase II |  |  |  | Phase III | 
 | 1. National coverage (all site types) (%) |  | 2. Sufficiency index (%) |  | 3. National coverage (adopted sites) (%) |  | 4. Proportion of adopted sites with management plans (%) | 
 | OPTIMISTIC | REALISTIC | OPTIMISTIC | REALISTIC | OPTIMISTIC | REALISTIC | OPTIMISTIC | REALISTIC
Baseline (2020) | 14.8 | 14.8 | 21.7 | 21.7 | 4.7 | 4.7 | 13.5 | 13.5
Mid-term target (2025) | Tbd | Tbd | Tbd | Tbd | Tbd | Tbd | Tbd | Tbd
Final target (2030) | Tbd | Tbd | Tbd | Tbd | Tbd | Tbd | Tbd | Tbd

## Slide 4
Level of ambition of 2030 targets
Post-2020 workplan needs measurable targets and associated indicators
Optimistic and realistic approaches?
Optimistic: comparable to the EU committments to the Global Biodiversity Framework: «Legally protect a minimum of 30% of the land area and 30% of the sea area»? But the role of Natura 2000/Emerald is uncertain!
Realistic: Natura 2000 performance indicators in 2016?
Targets not decided. Discussion will continue in 2021

## Slide 5
Table 2. Strategic issues [short]
Phase | No. | Description
General | 0-1 | Develop Emerald Network IT tools
 | 0-2 0-3 | Develop and update the Emerald Network barometer Update the list of habitats in Resolotion 4
Phase I | I-1 | Enquiry to all non-EU countries about lack of progress
 | I-2 | Explain the benefits of running the Emerald Network process before Natura 2000
Phase II | II-1 | Need for regularity of bio-geographical seminars or bilateral meetings
 | II-2 | Need for preparatory meetings after long inactivity period
 | II-3 | Need for bilateral evaluation meetings with individual countries
 | II-4 | Need for special assistance projects
 | II-5 | Need for marine bio-geographical seminars (in future)
Phase III | III-1 | Need for information exchange forum on site management
 | III-2 | Need for systematic data about management plans in Emerald site databases

## Slide 6
3. Strategic framework

## Slide 8
Appendix. Framework for detailed planning

## Slide 9
Concluding remarks
This is proposal applies to general principles and the structure of the workplan
But it (particularly targets) should be further developed in 2021, in the light of CBD’s Global targets anf EU interpretive guidance on EU Biodiversity Strategy 2030