## Slide 1: The World Bank Project: Combating Cybercrime- Tools and Capacity Building for Emerging Economies
OCTOPUS 2015, Council of Europe
Jinyong Chung

## Slide 2: Project Overview
Timing 1 July 2014 / Two Years funded by Republic of Korea
Mission To build capacity among policy-makers, legislators, public prosecutors & investigators, and civil society in developing countries
in the policy, legal and criminal justice aspects of the enabling environment to combat “cybercrime”;
through synthesizing international best practice in these areas in a published tool that enables assessment of and best practice guidance with respect to the legal issues associated with combatting cybercrime; and field testing the tool in selected pilot countries.
Partners Council of Europe ITU UNODC UNCTAD UNICRI
Korean Supreme Prosecutors’ Office Oxford University AIDP

## Slide 3: Project Progress
Phase 1
(FY 15)
Phase 2
(FY 16)
Develop Country Selection Criteria
Develop List of Candidate Countries
Due Diligence on Best Practices
Due diligence on Capacity Building Programs
Project Planning Meeting; Confirm Roles of GFLJD Partners in specific activities
Select Pilot
Countries
Agree Tool & methodology, content
Conduct Assessments
Country Feedback
Draft Content Tool
Final Tool / Content
Final Content,
On-Line Launch
Partner Consultation
Partner Consultation
Partner Consultation
Partner Consultation
Select Consultant for on-line content
Beta Version for on-line “frames”
1 Jan ‘15
1 July ‘15

## Slide 4: Toolkit for Initial Self Assessment
Purpose
  Initial self assessment tool for each countries
  Platform for int’l cooperation for strategy establishment
Method
  Synthesize any existing guidelines by each partners with evaluation
  Open to public as a public goods and for updates
Process
  By June 2015
    Develop Basic Template (Key concepts – Analyzing present status – Best Practices – conclusion)
    Kick off with certain fields and partners review
  By Sep 2015
    Develop each section of Tool Kits and put together for Draft Tool Kit
  By June 2016
    Apply to Pilot countries and Finalize

## Slide 5: Proposed Structure for Toolkit

## Slide 6: Application of Toolkit – Self Initial Assessment

## Slide 7: Lessons Learnt
Collaboration
  Synthesizing Exits Knowledge/Knowhow
  Catch up Progress of Cybercrime
Practicality
  Not only Theory, But also Applicability
  High-tech response against high-tech attack
Client Engagement
  PPP
  Host Countries Involvement
Next Step
  Collect, Accept and Reflect Fields
  Be concise and to the Point

## Slide 8: Thank you
Jinyong Chung
jchung3@worldbank.org