CALL FOR PROPOSALS

GRANT FOR ROMACTEDII SUPPORT ORGANISATION  FOR THE IMPLEMENTATION OF ACTIVITIES IN PODGORICA – CAMP KONIK

ROMACTEDII/2021/GRANTS/01

| Project | Joint EU/CoE Programme ROMACTEDII |
| --- | --- |
| Awarding entity | Council of Europe |
|  | Directorate General of Democracy, Anti-Discrimination Directorate, Roma and Travellers Team, and the Office of the Directorate General for Programmes (ODGP) |
| Funding | Joint EU/CoE Programme ROMACTEDII |
| Duration | Projects shall be implemented for a maximum of 24 months between 01 November 2021 and 31 October 2023. |
| Estimated starting date | 01 November 2021 |
| Issuance date | 01 September 2021 |
| Deadline for applications | 30 September 2021 |

TABLE OF CONTENTS

I.	INTRODUCTION	3

II.	BACKGROUND INFORMATION ON THE COUNCIL OF EUROPE PROJECT	3

III.	BUDGET AVAILABLE	4

IV.	REQUIREMENTS	4

1.	General objective	4

2.	Means of action	5

3.	Implementation period	6

4.	Target stakeholders	6

5.	Budgetary requirements	6

6.	Further to the general objective, preference will be given to:	7

7.	The following types of action will not be considered:	7

8.	Funding conditions:	7

9.	Reporting requirements:	7

V.	HOW TO APPLY?	8

1.	Documents to be submitted:	8

2.	Questions	8

3.	Deadline for submission	9

4.	Change, alteration and modification of the application file	9

VI.	EVALUATION AND SELECTION PROCEDURE	9

1.	Exclusion criteria:	9

2.	Eligibility criteria:	10

3.	Award criteria	10

VII.	NOTIFICATION OF THE DECISION AND SIGNATURE OF GRANT AGREEMENTS	11

VIII.	INDICATIVE TIMETABLE	11

Appendices:

- Appendix I - Application Form

- Appendix II - Provisional budget (Template)

- Appendix III - Template Grant Agreement (for information only)

How to apply?

- Complete and sign the Application Form in English (See Appendix I)

- Attach a provisional budget in Excel (using the template reproduced in Appendix II)

- Attach the other supporting documents:

- Document certifying the registration of the NGO/civil society organisation/entity with a courtesy translation in English ;

- Bank/financial statements authorised by a financial officer of the NGO/civil society organisation/entity;

- CV of the proposed Coordinator and the proposed Facilitator, both in English, and clearly indicating the formal links with the organisation;

- Contact details of referees;

- A work plan setting out proposed activities in English.

- Send these documents in electronic form (Word, Excel and/or PDF) to the following e-mail address: romacted@coe.int. Emails should contain the following reference in subject: ROMACTEDII Grants – Call for Proposals Montenegro Camp Konik.

- Applications must be received before 30 September 2020 at 23:59 CET.

- INTRODUCTION

This call for proposals is launched within the framework of the Council of Europe/European Commission ROMACTEDII Programme: “Promoting good governance and Roma empowerment at local level”. The ROMACTEDII Programme aims to co-fund projects in seven beneficiaries in the Western Balkans + Turkey using the ROMACTED methodology with the ultimate aim of building up political will and understanding of Roma inclusion at local level. More information on the ROMACTED Programme is available at http://coe-romacted.org.

Project proposals must use the ROMACTED methodology which is outlined in the ROMACTED Handbook available here.

For additional reading, please note that the ROMACTED methodology is a combination of the ROMED2 and ROMACT methodologies which are available online as follows: ROMED2 Guidelines for National and Local Facilitators (here) and ROMACT handbook (here).

Project proposals shall aim to produce an added value to the Council of Europe’s efforts in this domain, as set out further in Section IV below.

- BACKGROUND INFORMATION ON THE COUNCIL OF EUROPE PROGRAMME

The purpose of the current call for proposals is to select a Support Organisation in Montenegro to provide support to the Council of Europe in carrying out activities in Podgorica - Camp Konik, according to the adapted methodology, and considering the specifics that this settlement has. Camp Konik has hosted thousands of Roma and Egyptian displaced persons for more than two decades (1,869 people - 357 households, including in private accommodation). During these years, the Government of Montenegro, the EU and other donors, supported by the Regional Housing Programme, have helped these persons acquire better living conditions, providing new housing units for every family settled in the camp area. However, still today, most of the families in Konik living in the new buildings, do not have a permanent income to enable them to fulfil their financial obligations such as paying electricity and water bills, garbage collection, etc. For some of them, this is the reason why they fail to adequately maintain the living space and common areas. On the other hand, a certain number of families unfortunately has shown negligence in maintaining their flats and common areas in an appropriate way, which has led to the presence of dirt and garbage, broken doors, etc. In addition to the issue linked to the management of the new houses/buildings, the Roma and Egyptian population in Konik is still impacted by various socio-economic and health difficulties, such as a lack of proper school education, professional skills and job qualifications which cause high early drop-out rates from school and unemployment; a lack of financial means to buy food and basic necessities; social issues connected with child-begging, early marriages, human trafficking, and family violence; and finally, little health awareness which results in low life expectancy, as well as a high rate of infectious diseases and non-communicable diseases.

The action will follow a participatory process with community mobilisation and engagement at its heart, and through close cooperation with the representatives of the Capital of Podgorica which has legal obligations in these matters.

The Support Organisation selected through this call shall primarily provide organisational and logistical support and assistance in order to enable the smooth running of all activities in Camp Konik, in a way which adds value to the programme. Applicants should be prominent Roma or other civil society organisations and qualified entities with a very good track record in working on Roma inclusion, community empowerment processes, with vulnerable groups, with governments at local and central level, and having adequately experienced and knowledgeable staff/experts within its structures, recognised by the central and in particular local governments as a partner.

Applicants shall put forward the name of one Coordinator from among its staff who possesses the necessary requirements for the co-ordination and implementation of the stated objectives (see further Section IV, Requirements, below). For that purpose, the applicant shall propose a candidate in their application form, and submit a CV of the candidate. The necessary costs of the coordinator allocated on a maximum of 25% basis to the ROMACTEDII Programme will be included in the budget proposal of the applicant.

In addition, the applicant shall put forward the name of at least one Facilitator from among its staff or the community who possesses the necessary requirements for the co-ordination and implementation of the stated objectives (see further Section IV, Requirements, below). For that purpose, the applicant shall propose a candidate in their application form, and submit a CV of the candidate. The necessary costs of the facilitator allocated on a maximum of 50% basis to the ROMACTEDII Programme will be included in the budget proposal of the applicant.

Further detail on the types of activities eligible for financial support is set out below under “means of action”.

- BUDGET AVAILABLE

The Council of Europe intends to award one grant of between 20,000 EUR (minimum) to 30,000 EUR (maximum).

Subject to availability of funds and extension of the Project’s initial duration, the Council of Europe reserves the right not to award all available funds, and/or to redistribute the available funds in a different manner depending on the project proposals received and on the outcome of the call for proposals.

- REQUIREMENTS

- General objective

The grant will fund projects designed to assist the Support Team in  Montenegro with the implementation of the ROMACTED methodology by providing organisational and logistical support activities in Podgorica – Camp Konik.

The objectives and results to be obtained with the financial support are as follows:

Objective(s) (outcomes):

- Strengthen the capacity of the Roma community to participate more actively in decision-making processes related to them, but also to take on their responsibilities;

- Improve the capacity of local authorities to perform their roles and responsibilities in an effective and efficient manner when it comes to designing and implementing plans, policies and projects, in particular active inclusion measures that improve Roma integration;

- Improve the efficiency, effectiveness and sustainability of local policies, measures and delivery of services.

Results (outputs):

- Getting local authorities committed to including their Roma population;

- Development of Local Action Plan for Roma integration

- Getting the Roma community mobilised;

- Defining the needs and priorities to improve living conditions of Roma community;

- Translating the priorities into action plans;

- Funding, implementing and monitoring.

Possible areas of intervention:

- Housing: Raising the awareness of the inhabitants of buildings about the importance of proper maintenance of apartments, buildings, and other common areas;

- Work with other community members: Special meetings with women and young people to identify their needs and problems, strengthen them for more active participation in society, and resolve their needs and concerns;

- Bringing communities together: To reduce the gap between Roma and non-Roma.

- Means of action

Projects may include the following activities which the Support Organisation will, amongst other things, set up, organise and follow up, based on its proposed plan of activities, in accordance with the ROMACTED methodology:

- Establishment of Community Action Groups and other necessary working groups, in accordance with the methodology;

- Organisation of workshops, meetings, conferences, training sessions, seminars, coaching sessions and similar events at local level primarily;

- Organisation of bilateral meetings with Roma communities, local authorities and other relevant stakeholders.

- Organisation and conducting of surveys, mapping, research (for example, community needs assessment and identification, capacity needs assessment for local authorities, baseline surveys, needs for expert support, assessment of funding opportunities);

- Necessary communication in order to achieve the results and steps, including and not limited to: the appointment of a coordinator, signing of letters of commitment by local authorities, establishment of working groups;

- Drafting and developing joint plans of action, concrete actions, priorities lists, project proposals;

- Celebrating International Roma Day;

- Joint activities of Roma and non-Roma communities, for example, camp cleaning, excursions, sports events, etc;

- Visibility actions.

Any other action pursuing the above objectives and results or related to the Community Action Groups’ (CAG) list of priorities.

Role of the Coordinator (allocated on a 25% basis to ROMACTEDII):

Within the framework of the possible activities as described above, the ROMACTED Coordinator will have the responsibility to coordinate, monitor and assist the quality of work at the level of Podgorica, working in close coordination with the CoE ROMACTED Project Officer in Montenegro and the ROMACTED Team in Strasbourg.

In particular the role of the Coordinator will be to:

- Perform specific tasks of coordination and monitoring of the action with the aim of improving the responsiveness and accountability of local authorities, particularly elected officials and senior civil servants, towards marginalised Roma communities and extract learning from the process;

- Establish working relations and regular contacts with local authorities, Community Action Groups and other local stakeholders within the Programme’s municipalities;

- Prepare for and represent the Support Organisation in specific meetings at local level and the Programme’s Advisory Group in Montenegro;

- Provide quality control and guidance to the Facilitator(s) to ensure the adequacy of approaching the different local situations and adapting the methods accordingly. This will help to identify deviations from the approach and quickly fix situations which are in conflict with the ROMACTED philosophy;

- Submit the narrative reports, including the Trimestral Narrative Report at the level of Podgorica and the Trimestral Municipal Reports through the online reporting system and in coherence with the guidelines provided by the CoE Secretariat;

- Prepare, process and record all financial transactions in a timely manner;

- Actively cooperate with the representatives of the Capital of Podgorica.

Applicants for the role of Coordinator should have at least 3 years’ experience working on Roma inclusion. Experience of working in Camp Konik will be considered as an asset.

Role of the Facilitator(s) (allocated on a 50% basis to ROMACTEDII):

- Identify and mobilise community members to engage in a participatory process and compose the Community Action Groups (CAGs), being particularly attentive to Roma women and youth, as well as Roma returnees if applicable;

- Undertake a facilitating function in relation to the implementation of project activities in Podgorica – Camp Konik, acting as a conduit between Roma communities and municipal authorities and identifying members to be involved in all local activities and supporting their participation;

- Draft and prepare work plan proposals for the implementation of project activities and provide input about structures, power relations and decision-making mechanisms at local level;

- Plan, organise and facilitate meetings within Podgorica - Camp Konik, in particular meetings of the Community Action Group (CAG), meetings with Local Administration (LA), and Municipal Taskforce meetings of same, as well as other events and activities;

- Assist public institution(s) in implementing decisions and commitments;

- Identify needs for capacity development and technical assistance to stakeholders at local level, including local level training and coaching (CAG and LA), planning and organising training, workshops and roundtables, securing the participation of local partners/speakers and ensuring the quality and relevance of these activities, proposing improvements where necessary;

- Attend events at municipal level, such as preparatory meetings, conferences, workshops, trainings, meetings organised by local NGOs, international organisations or donor organisations;

- Research and collect information about municipal action plans/local development plans/initiatives, surveys and assessments, relevant developments in the field of social inclusion and work with vulnerable groups in the relevant municipality(ies) and other relevant developments, for the improvement, adjustment, development of ROMACTED strategy and work plans at municipal levels.Applicants for the role of Facilitator should have at least 3 years’ experience working on Roma inclusion. Experience of working in Camp Konik will be considered as an asset.

- Implementation period

The implementation period of the Project should start on 1 November 2021 (see indicative timetable under VIII. below) and end on 31 October 2023. If the Programme is extended by the donor, this implementation period may be extended, subject to written agreement between the Council and the Grantee.

Reporting requirements shall be completed by 30 November 2023 at the latest.

- Budgetary requirements

Project proposals shall be accompanied by a draft budget (See Template Budget, in Appendix II) amounting to a maximum of 30,000 EUR (thirty thousand Euros). The estimated budget must be consistent, accurate, clear, complete and cost-effective, in the light of the activities proposed.

Each Grantee shall also be required to contribute to the project either by way of its own resources or by contribution from third parties. Co-financing may take the form of financial or human resources, in-kind contributions or income generated by the action or project.

The proposed co-financing should be set out in the Application Form (Appendix I) and in the table at the top of the Draft Budget (Appendix II).

The cost of human resources must not exceed 60% of the total budget.

- The following types of action will not be considered:

- Projects/actions providing financial support to third parties (re-granting schemes);

- Projects/actions concerning only or mainly individual scholarships for studies or training courses;

- Projects/actions supporting political parties.

- Funding conditions:

The funds for the grant should in principle be distributed as follows:

- 45 % will be paid to the Grantee or the Lead Grantee, in case of a consortium, when the Grant Agreement between the two parties is signed;

- 45% representing a second instalment after the submission and acceptance by the Council of Europe of the first annual interim financial report after 12 months of implementation;

- the balance of 10% will be paid to the Grantee or the Lead Grantee, in case of a consortium, based on actual expenditure incurred, and after the presentation and acceptance by the Council of Europe of the final narrative and financial reports for the Grant implementation.

- Reporting requirements:

- Narrative reporting requires:

  - a full narrative report to be submitted by the deadline indicated above, in section 3, on the use made of the grant and a copy of the register of the persons present during each of the activities, including names and signatures of participants;

  - a trimestral narrative report (every three months) to be submitted by the Coordinator using the ROMACTED Programme’s online reporting system.

- Financial reporting requires:

- a first annual interim financial report in Excel format and including full financial paperwork after 12 months of implementation;

- a final financial report to be submitted by the deadline indicated above, in Section 3.

Financial reporting requires in particular a statement in the currency in which the Grant Agreement will be concluded (Euros or local currency), in English, stating the payments made for the implementation of the activities, certified by the responsible financial officer of the Grantee, accompanied by “appropriate original supporting documents” (see below). The Council of Europe reserves the right to ask for summary translations of invoices into English. If for legal reasons the original documents must be retained by the Grantee, certified copies must be submitted with the financial statement.

“Appropriate original supporting documents” refers to signed contracts, invoices and acceptances of work (for all transactions), payment authorisation for all transactions should also be provided in case the Grantee uses such practice, and reliable evidence of payment (authorised payment order and bank statement).

As regards round tables / conferences, presenting “appropriate original supporting documents” requires presentation of a programme indicating the title, dates, venue, and agenda of the event; the names of persons facilitating the event, a signed list of participants, the contracts with the owner of venue of the event (e.g. hotel) for the rent of premises, food and beverages of participants, invoices from the owner of the venue of the event for the above services, and a report on the results of the event (see narrative reporting above).

As regards consultancy services, presenting “appropriate original supporting documents” requires presentation of evidence of the outputs produced, contracts with experts and consultants containing a specific description of services to be carried out, invoices produced after the works have been performed and delivered (the specialities of the consultants shall correspond to the nature of activities for which they are contracted).

As regards travel fees / lodging of experts and participants, presenting “appropriate original supporting documents” requires presentation, where relevant, of contracts with a travel agency for travel fees and lodging, invoices of the travel agency indicating destinations, dates, ticket costs, and names of the travelling persons, a programme of the event indicating the names of the experts and signed lists of participants.

The above description is not comprehensive. Any doubt regarding the interpretation of the notion of “appropriate original supporting documents” should lead the Grantee or the Lead Grantee, in case of a consortium, to consult the Council of Europe.

NOTE: Financial documentation must be available to the ROMACTED Project Officer when requested for inspection as part of regular monitoring of the implementation of activities.

- HOW TO APPLY?

- Documents to be submitted:

Each application shall contain:

- the completed and signed Application Form in English (See Appendix I);

- a provisional budget (using the template reproduced in Appendix II);

- a document certifying the registration of the NGO/civil society organisation/entity with a courtesy translation in English;

- bank /financial statements authorised by a financial officer of the NGO/civil society organisation/entity;

- CV of the proposed Coordinator and the proposed Facilitator, both in English, and clearly indicating the links with the organisation;

- Contact details of two referees;

- A work plan setting out proposed activities in English.

If any of the documents listed above are missing, the Council of Europe reserves the right to reject the application.

- Questions

General information concerning the ROMACTED Programme and the work of the Council of Europe on Roma issues can be found on the following websites: http://www.coe-romacted.org and http://www.coe.int/roma.

Other questions regarding this specific call for proposals must be sent at the latest one week before the deadline for the submission of proposals, in English, and shall be exclusively sent to the following address: romacted@coe.int, with the following reference in subject: ROMACTEDII Grant Montenegro Camp Konik – Questions.

- Deadline for submission

The application form, completed and signed, together with the supporting documents (including the provisional budget in Excel), must be submitted in electronic form (Word, Excel and/or PDF) to the following e-mail address: romacted@coe.int. Emails should contain the following reference in subject: ROMACTEDII Grant – Call for Proposals Montenegro Camp Konik.

Applications must be received before 30 September 2021 23:59 CET. Applications received after the above mentioned date will not be considered.

- Change, alteration and modification of the application file

Any change in the format, or any alteration or modification of the original application file, will cause the immediate rejection of the application concerned.

- EVALUATION AND SELECTION PROCEDURE

The projects presented will be assessed by an Evaluation Committee composed of three Council of Europe staff members.

The procedure shall be based on the underlying principles of grant award procedures, which are transparency, non-retroactivity, non-cumulative awards, not-for-profit, co-financing and non-discrimination, in accordance with Rule 1374 of 16 December 2015 on the grant award procedures of the Council of Europe.

The applicants, and their projects, shall take into account all of the following criteria:

- Exclusion criteria:

Applicants shall be excluded from the grant award procedure where they:

- have been sentenced by final judgment on one or more of the following charges: participation in a criminal organisation, corruption, fraud, money laundering, terrorist financing, terrorist offences or offences linked to terrorist activities, child labour or trafficking in human beings;

- are in a situation of bankruptcy, liquidation, termination of activity, insolvency or arrangement with creditors or any like situation arising from a procedure of the same kind, or are subject to a procedure of the same kind;

- have received a judgement with res judicata force, finding an offence that affects their professional integrity or constitutes a serious professional misconduct;

- do not comply with their obligations as regards payment of social security contributions, taxes and dues, according to the statutory provisions of the country where they are established;

- are an entity created to circumvent tax, social or other legal obligations (empty shell company), have ever created or are in the process of creation of such an entity;

- have been involved in mismanagement of the Council of Europe funds or public funds;

- are included in the lists of persons or entities subject to restrictive measures applied by the European Union (available at www.sanctionsmap.eu).

By signing the Application Form, applicants shall declare on their honour that they are not in any of the above-mentioned situations (See Appendix I, Item 14).

The Council of Europe reserves the right to ask applicants at a later stage to supply the following supporting documents:

- for the items set out in paragraphs a), b) and c), an extract from the record of convictions or failing that an equivalent document issued by the competent judicial or administrative authority of the country where the applicant is established, indicating that these requirements are met;

- for the items set out in paragraph d), a certificate issued by the competent authority of the country of establishment;

- for the items set out in paragraph e);

  - for natural persons, a scanned copy of a valid photographic proof of identity (e.g. passport)

  - for legal persons, an extract from the companies register or other official document proving ownership and control of the applicant.

- Eligibility criteria:

In order to be eligible for a grant, an applicant must:

- be legally constituted as a NGO/civil society organisation/entity in Montenegro;

- be entitled to carry out in Montenegro activities described in its project proposal;

- have been active for at least three years in the field of Roma inclusion, Roma communities, policies, public administration, access to funding, and social inclusion;

- have experience in work with the Roma community in Camp Konik;

- have sufficient financial capacity (stable and sufficient sources of funding) to maintain its activity throughout the period for which the grant is awarded and to participate by way of its own resources (including human resources or in-kind contributions);

- have sufficient operational and professional capacity, including staff, to carry out activities described in  its project proposal;

- propose a Coordinator who has at least 3 years of experience working on Roma inclusion;

- propose a Facilitator who has at least 3 years of experience in a similar role;

- have a bank account.

Multiple applications are not allowed and shall lead to the exclusion of all applications concerned.

- Award criteria

Applications will be assessed against the following criteria:

- the relevance and added value of the project with regard to the objective of the call, having regard in particular to the applicant’s already established contacts and relations with local authorities, Roma communities and other stakeholders which may facilitate implementation and further programme development. Requirements, Section 4. Target Stakeholders (25%);

- the extent to which the action meets the requirements of the call, in particular with regards to the use of the ROMACTED methodology (20%);

- the quality, accuracy, clarity, completeness and cost-effectiveness of the application and the estimated budget (25%);

- the relevance of the experience of the applying organisation(s) and its staff, including the proposed Coordinator and proposed Facilitator(s), including in particular experience working with Roma community. and local authorities in Podgorica, and experience working with similar methodologies in other projects (30%). Experience of working in Camp Konik will be considered as an asset.

While taking into account the above criteria, the exact amount of financial support for the Grantee will be determined on the basis in particular of:

- The quality, accuracy, completeness and cost-effectiveness of the project proposal including the budget received from the applicant through the call for proposals;

- Historical data from the implementation of similar programmes and other similar programmes implemented by CoE, if any.

- NOTIFICATION OF THE DECISION AND SIGNATURE OF GRANT AGREEMENTS

On completion of the selection process, all applicants will be notified in writing of the final decision concerning their respective applications as well as on the next steps to be undertaken.

The selected Grantee will be invited to sign a Grant Agreement (See Appendix III, for information only), formalising their legal commitments. Potential applicants are strongly advised to read the draft contract, in particular its requirements in terms of payment and reporting.

- INDICATIVE TIMETABLE

| Phases | Indicative timing |
| --- | --- |
| Publication of the call | 1 September 2021 |
| Deadline for submitting applications | 30 September 2021 |
| Information to applicants on the results of the award procedure | 15 October 2021 |
| Signature of the grant agreements | 25 October 2021 |
| Implementation period | 01 November 2021 – 31 October 2023 |

* * *

Authorities at central and local level, local Roma communities and key central entities related to Roma issues, for example, Contact Points for National Roma Inclusion Strategies, Managing Authorities of European Social Funds and other EU funds.